## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
프로젝트: 그린 밥상을 부탁해~
팀 구성원: | 우상호, 홍지원, 고상현, 최성덕,
프로젝트 시작일: | 2023-09-22 | [10 empty] | Scrolling increment: | [5 empty] | 13
[5 empty] | October | [27 empty] | November
 | time axis 2023-10-05 to 2023-11-29
작업제목 | 담당자 | 진행상태 | 시작일 | 경과시간 | time axis 2023-10-05 to 2023-11-29
아이디어 선정
아이디어 선정 |  | 100% | 2023-09-25 | 2 | bar: 2023-10-25
카카오오븐 | 고상현 | 100% | 2023-09-25 | 2 | bar: 2023-10-25
DB다이어그램 | 홍지원 | 20% | 2023-09-22 | 2
프로젝트 기간구상 |  | 100% | 2023-10-15 | 1
간트차트 작성 | 우상호 | 10% | 2023-10-01 | 6
게시판
초기 페이지 |  | 60% | 2023-10-01 | 13
회원가입 |  | 50% | 2023-10-02 | 9
커뮤니티 |  | 33% | 2023-10-10 | 11
리빙팁 |  |  | 2023-10-19 | 1
공지사항 |  |  | 2023-10-20 | 24
DB
식약처 레시피 등록 |  |  | 2023-10-10 | 4
|  |  | 2023-10-14 | 14
Design proposal |  |  | 2023-10-30 | 6
Materials |  |  | 2023-11-12 | 3
Equipment |  |  | 2023-11-04 | 19
Testing
Environment |  |  | 2023-11-01 | 15
System test |  |  | 2023-10-24 | 5
Issues/bugs |  |  | 2023-12-14 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2023-09-22 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [27 empty] | November
 | time axis 2023-10-05 to 2023-11-29
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-10-05 to 2023-11-29
Title 1
Task 1 |  | 25% | 2023-09-25 | 3
Task 2 |  |  | 2023-09-30 | 1
Task 3 |  | 50% | 2023-09-22 | 10
Task 4 |  |  | 2023-10-15 | 1 | bar: 2023-10-15
Task 5 |  | 10% | 2023-10-01 | 6
Title 2
Task 1 |  | 60% | 2023-10-01 | 13
Task 2 |  | 50% | 2023-10-02 | 9
Task 3 |  | 33% | 2023-10-10 | 11
Task 4 |  |  | 2023-10-19 | 1 | bar: 2023-10-19
Task 5 |  |  | 2023-10-20 | 24
Title 3
Task 1 |  |  | 2023-10-10 | 4
Task 2 |  |  | 2023-10-14 | 14
Task 3 |  |  | 2023-10-30 | 6
Task 4 |  |  | 2023-11-12 | 3
Task 5 |  |  | 2023-11-04 | 19
Title 4
Task 1 |  |  | 2023-11-01 | 15
Task 2 |  |  | 2023-10-24 | 5
Task 3 |  |  | 2023-12-14 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2023-09-22 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | October | [27 empty] | November
 | time axis 2023-10-05 to 2023-11-29
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-10-05 to 2023-11-29
Title 1
Task 1 |  | 25% | 2023-09-25 | 3
Task 2 |  |  | 2023-09-30 | 1
Task 3 |  | 50% | 2023-09-22 | 10
Task 4 |  |  | 2023-10-15 | 1 | bar: 2023-10-15
Task 5 |  | 10% | 2023-10-01 | 6
Title 2
Task 1 |  | 60% | 2023-10-01 | 13
Task 2 |  | 50% | 2023-10-02 | 9
Task 3 |  | 33% | 2023-10-10 | 11
Task 4 |  |  | 2023-10-19 | 1 | bar: 2023-10-19
Task 5 |  |  | 2023-10-20 | 24
Title 3
Task 1 |  |  | 2023-10-10 | 4
Task 2 |  |  | 2023-10-14 | 14
Task 3 |  |  | 2023-10-30 | 6
Task 4 |  |  | 2023-11-12 | 3
Task 5 |  |  | 2023-11-04 | 19
Title 4
Task 1 |  |  | 2023-11-01 | 15
Task 2 |  |  | 2023-10-24 | 5
Task 3 |  |  | 2023-12-14 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one